## Sheet1
List of tasks |  |  | Assigned to | Expected date to complete | Actual date of complete | Remarks
Problem definition |  |  | All | 2020-11-21
Requirement Specification | Hardware Requirements |  | All | 2020-11-25 | 2020-11-27
| Software requirements |  | All | 2020-11-27
Design | High level design | Block diagram for system | Asha | 2020-12-03 | 2020-12-04
|  | Block diagram for hardware | Lakshmisha and Unmesh | 2020-12-03 | 2020-12-04
|  | Block diagram for software | Asha and Lakshmi Narayana | 2020-12-03 | 2020-12-04
| Detailed Level design | Source | Lakshmisha | 2020-12-03 | 2020-12-05
Selected range and type of measurement has to be set
|  | Sinosoidal wave root(2)*Vrms*sin(2*pi*f*t) |  | 2020-12-03
AC main voltage:230V rms 50Hz.
|  | You find Vmax. |  | 2020-12-04 | 2020-12-09
Find Attenuation factor.
|  | Set ADC Ref.Voltage. |  | 2020-12-05
Step down to 5V Peak to Peak.
|  | Configurator | Asha | 2020-12-02 | 12/2/2020
Design GUI for selecting type of measurement like AC voltage and Voltage DC
Design GUI for selecting range and type of measurement
|  | Attenuator/Amplifier | Lakshmisha | 2020-12-09 | 2020-12-09
Attenuator will amplify or de-amplify the signal as per ADC input range as per configurator input
|  | ADC | Lakshmisha | 2020-12-11 | 2020-12-11
Adding Harmonic noise.
Use sampling at 1kHz.
|  | Output will be (root(2)*Vrms*sin(2*pi*f*t)*1/attenuation factor)+Asin(2*pi*f1*t) noise signal |  | 2020-12-12
|  | Filter | Unmesh | 2020-12-05 | 2020-12-08
Sample for 5 waves.
|  | So, calculate No of samples generated per each wave. |  | 2020-12-08
Then, calculate samples for 5 waves.
|  | Find the filter co-efficient. |  | 2020-12-12
|  | Determine Suitable Filter Design |  | 2020-12-12
|  | Calculate RMS for 5waves root VRMS = √(V12+ V22+ V32+ V42+ V52+ V62+……+ VN2)/N |  | 2020-12-14
|  | Data serialization | Lakshmi Narayana | 2020-12-05 | 2020-06-12
|  | Output to socket |  | 2020-12-04 | 2020-05-12
|  | Input from socket |  | 2020-12-04 | 2020-05-12
|  | Data deserialization |  | 2020-12-05 | 2020-06-12
|  | Measurement calculations | Unmesh | 2020-12-09 | 2020-12-12
Conversion of digital data to physical quantity value
|  | Display | Asha | 2020-12-01 | 2020-12-01
Design display to print the calculated value
Design display to print selected range and type of measurment
Implementation | Configurator | Implement GUI for selecting type of measurement like AC Voltage and DC Voltage | Asha | 2020-12-08 | 2020-12-09
|  | Implement GUI for selecting range and type of measurement |  | 2020-12-09
| Source | Selected range and type of measurement has to be set | Lakshmisha | 2020-12-11 | 2020-12-10
|  | Sinosoidal wave root(2)*Vrms*sin(2*pi*f*t) |  | 2020-12-15
AC main voltage:230V rms 50Hz.
You find Vmax.
Find Attenuation factor.
|  | Set ADC Ref.Voltage. |  | 2020-12-16
Step down to 5V Peak to Peak.
| Attenuator/Amplifier | Attenuator will amplify or de-amplify the signal as per ADC input range as per configurator input | Lakshmisha | 2020-12-17 | 2020-12-11
| ADC | Adding Harmonic noise. | Lakshmisha | 2020-12-19
Use sampling at 1kHz.
Output will be (root(2)*Vrms*sin(2*pi*f*t)*1/attenuation factor)+Asin(2*pi*f1*t) noise signal
| Filter | Sample for 5 waves. | Unmesh | 2020-12-19 | 2020-12-12
So, calculate No of samples generated per each wave.
Then, calculate samples for 5 waves.
Find the filter co-efficient.
Perform FFT(fast fourier transform) using butterfly diagram.
Calculate RMS for 5waves root VRMS = √(V12+ V22+ V32+ V42+ V52+ V62+……+ VN2)/N
| Data serialization | Convert data into serial bits | Lakshmi Narayana | 2020-12-12 | 15/12/2020
| Output to socket | Socket Communication using python code |  | 2020-12-15 | 17/12/2020
|  | Send bits to socket |  | 2020-12-15 | 17/12/2020
| Input from socket | Receive the bits from socket and send it to deserialization |  | 2020-12-15 | 17/12/2020
| Data deserialization | Conver serial bits into data |  | 2020-12-12 | 15/12/2020
| Measurement calculations | Conversion of digital data to physical quantity value | Unmesh | 2020-12-19 | 2020-12-14
| Display | Implemet GUI to display the result of measurement calculation | Asha | 2020-12-12 | 2020-12-19
|  | Implement GUI to display the selected range and type of measurement |  | 2020-12-12 | 2020-12-19
Design documentation | ADC | Designing of ADC | Lakshmisha | 2020-12-05 | 2020-12-22
|  | Derivation |  | 12/5/202
| Filter | Designing of Filter | Unmesh | 2020-12-05 | 2020-12-22
Filter Parameters
Testing report |  |  | Asha | 2020-12-19